## Integration Issues
To log all Integration issues found during the Pilot
Keep it Simple but we need to know what has already been spotted/fixed etc.
ID | Exchange/MDM | Logged By | Logged Date | User(s) Affected | Description | Severity | Assigned To | Comments/Progress | Status | Notes Record Link | Updated
I1 | Exchange | Ross | 2015-06-11 | All users | No GAL, hence unable to email other users | P1 | Rich L | 12/6: Attempting to lookup against Notes NCD 15/6: Will put a lookup into the build to use Notes NCD 15/6: Achieved - LDAP lookup creates the Address File. 17/6: Beware there is an approx 24 hour lag between the mailbox being created and an entry in the GAL for the user. | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/5E9DA2DF48BCADD080257E680046F171
I2 | MDM | Ross | 2015-06-12 | All MDM users | Unable to connect iPads/iPhones from internal Npt to Titchfield DMZ via WAN so can't get to Exchange. | P1 | Ross | 12/6: Mike M asked to expedite potential urgent WAN change via BT 17/6: Darren escalated within BT and Rebecca Clarke BT Global Services (07715 698217) putting Engineer in touch with Ross to ensure exact needs are known. 17/6: Confusion within BT not realising this is separate change - being clarified. 26/6: BT made change - Rich L and Keith to test on Monday am. | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/D2ED9FE1239AEEC180257E68003613DA
I3 | MDM | Phil H | 2015-06-12 | MDM users | There are some 77 iPad serial numbers on the asset mgt list that are not in the Airwatch lists implying they are not managed by Airwatch. Glen Watson's was an example. | P3 | Steve W | 12/6: Steve pulling the list of differences and names to validate how real the issue is. 17/6: Will be a task for the MDM Admin to trawl through and align asset numbers to users to Dep'ts. 29/7: Will control all iPads via the new Exchange roll out. | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/1C27BF0DEB5E9BAF80257E6800363616
I4 | Exchange | Rich L | 2015-06-15 | All users | DMZ Exchange Server crashed Sun and Mon - needs rebuilding | P1 | Rich L | 16/6: Was rebuilt and restarted am of 16/6. Monitor for any re-occurrence. | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/F69AB87891341A1180257E6800365271
I5 | Exchange | Phil H | 2015-06-15 | All users | In Outlook, select Address Book and Outlook goes into a hang state (not responding) - had to restart Outlook to resume after 10 mins waiting | P2 | Phil H | 15/6: Unable to reproduce. 15/6: Try again after I1 resolved above. 16/6: Outlook profile had become corrupted - potentially by deploying ad-hoc changes. Monitor for re-occurrence. | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/BB5BAA3EA8DD220F80257E6800365FAD
I6 | MDM | Jon Blake | 2015-06-15 | All MDM users | Can iPad users add their digital email addresses to the devices ? | P2 | Ross | 17/6: Phasing out digital email addresses but need to consider allowing iPads to use them short term. 17/6: See if can route digital addresses to exchange and that will be an acceptable workaround as digital email addresses are phased out. 29/6: Should be able to get to OWA for digital accounts in short term and route via BT/Vodafone in slower time. 29/7: iPads should be ready for testing later today. 02/09: Access to email will still be provided (via internet no Airwatch or mail app). 17/09 - Need to test this, to prove it works. iPad should be ready next week to test. | Investigation | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/9B853AAA6C1684AF80257E6800368B31
I7 | Exchange | Rich L | 2015-06-15 | All users | Application of AV to mail uncertainty of requirements | P2 | Ross | 15/6: Check with IA if satisfied to mirror Notes approach or other method required. 17/6: IA comfortable as SEGS perform virus checking but will need re-visiting post to the Wave 2 rollout. 29/7: This needs to be revisited 14th August. 19/08: The Antivirus solution for Exchange has been included with the Requirements for the next phase. This will ensure that AV is implemented across all Exchange servers. 02/09: Close - being designed as part of scaled out exchange solution | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/5A9828E4901E763E80257E68003699C0
I8 | MDM | Mike Martin | 2015-06-15 | All MDM users | Disabling bluetooth prevents connection to wireless keyboards | P3 | Keith C | Document policy via Keith's Airwatch settings and seek IA approval whether bluetooth can be enabled or not on iPads. 29/7: Katy to discuss with Keith Collier next week. 10/08: Katy has emailed Keith. 11/08: Response received; The current regulations from home office (End_User_Devices_Security_Guidance_-_Apple_iOS_8), shows that there was no methods to control wifi or Bluetooth, however as ONS is using AirWatch Mobile Device Management system, there is the capability to control the bluetooth interface, I am cc'ing Hywell of IA & Ceinwen to make them aware of this enquiry, as there is a need to manage this Bluetooth keyboard installation with care. 1/9: PRH - No explicit requirement to date to disable bluetooth. 02/09: This should be tested as part of roll out. IA will need to sign off. Katy will contact Hywel Lewis. 07/09: Katy discussed with Hywel. He is in agreeement and has provided the following; Using bluetooth for the Pilot is acceptable on the following basis: a) no authentication credentials to be input using bluetooth devices (ID / password / passcode) b) no sensitive information to be input using bluetooth devices (i.e. adhere to guidance for using OFFICIAL systems) c) a test should be undertaken as soon as practicable (next scheduled pen test) to assess the vulnerability of the bluetooth traffic to interception / injection. 10/09: Phil will discuss with Keith. 17/09: Phil has discussed with Keith, it won't be disabled. Phil needs to agree a policy with Hywel and comms need to ensure staff are aware of restrictions. | Investigation | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/599A00285BFD10B580257E680036AFBD
I9 | Exchange | Phil H | 2015-06-17 | 2 so far | When outlook is first installed - it is unable to connect to the Exchange Server (doesn't know the name) hence needs Richard L to manually configure. | P3 | Richard L | 16/6 - Julie Southan and 17/6 - Simon Taylor 17/6: Also on Ross' test machine. 30/6: Very rare | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/DEABC1ED1E6C031980257E680036C171
I10 | Exchange | Rich L | 2015-06-17 | All users | Exchange backup license needs checking and procured if necessary. | P2 | Ross | 17/6: Pilot workaround is for Export to flat file and backup that way - needs resolving for post Wave 2 (early July) as unsustainable as pilot usage grows. 02/09: Close - being designed as part of scaled out exchange solution | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/189F7D68A14A972180257E680036EBAD
I11 | MDM | Ross | 2015-06-17 | All MDM users | ASA verification check needed for the certificates. | tbd | Ross | 5/8: Ross has confirmed that this scheduled for possible resolution on 12th Aug. 02/09: Close. This has been done by BMS | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/4FA60C85EDA819BF80257E6800370683
I12 |  |  |  |  | Amend BMS laptop profile to guarantee iPads can't connect as laptops via ASA. | P1 | Ross | 5/8: Ross has confirmed that this scheduled for possible resolution on 12th Aug. 02/09: Close. This has been done by BMS | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/717F43D5A309744180257E68003719F8
I13 | Exchange | Derek T | 2015-06-16 | 2 so far | Both Sylvia Stevens and Julie Southan do not have ONS Directory available in Address Book drop down list | P2 | Ross | 16/6: Rich L pushed it to the client for these users but will need to work for wider rollouts. 23/6: Phil configured it on JS laptop manually. | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/6FAEC0FE1CF8970180257E6800374CFE
I14 | Exchange | Phil H | 2015-06-17 | 2 so far | If SCCM fails to complete (e.g. system restarted mid way) then need to manually restart the SCCM deployment. | P3 | Rhion | 17/6: Put check in place that user can start outlook before Rhion/Phil cut over primary email routing - otherwise will lose Notes mail as well until Outlook is properly installed for a user. 02/09: Migration plans will mitigate this | Implemented | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/A989DB296B9D9D3C80257E680037772E
I15 | Exchange | Rich L | 2015-06-17 | 1 so far | Windows update patches force a reboot affecting SCCM deployment of outlook. | P3 | Richard L | 17/6: WSUS patching monthly so avoid rolling out on that day if possible. 02/09: Migration plans will mitigate this | Investigation | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/9A79615EEA24847F80257E6800379E65
I16 | Exchange | Derek T | 2015-06-18 | DT & JS so far | A FAR named server is allocating itself to the user profile as an exchange server. This is affecting contact lists but may have other impacts | P2 | Richard L |  | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/24F873029EA18D4980257E680033E989
I17 | Exchange | Phil H | 2015-06-22 |  | When trying to access OWA some users can't resolve the url https:\\oa.ons.gov.uk/owa whereas some can - no obvious pattern. They can however access https://fa1rvwapxx398.ons.statistics.gov.uk/owa | P2 | Richard L | 23/6: The link did not resolve for Paul Jones (D1), but did for Phil Holding (D1), Umesh (Annexe) and his colleague (Annexe) each using their non-admin accounts. 10/08: Katy and a Notes user tested both links, both can access both links | Closed - MRO
I18 | Exchange | Phil H | 2015-06-25 | JS regularly and Ceinwen once to date | Outlook client lost connection to the Exchange Server on Julie's laptop on 25/6 at 11:45 and had failed to connect when starting up on 24/6 at approx. 7am. | P2 | Richard L | 25/6: Manually closing and restarting outlook cause it to reconnect correctly. No other users experiencing problems. 25/6: Ceinwen had it at 12:05 26/6: Julie regularly getting the interruption - can reconnect without always having to restart Outlook. 29/7: Wireless and LAN working simultaneously most lilely caused this issue | Closed - MRO | notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/C1CBD2688CBDAB9580257E6D003412CD
I19 | Exchange | Phil H | 2015-06-25 | Seems like all Pilot Exchange users | External parties when replying to ONS emails experience bounced messages citing an exchange mailbox. See link. This happened with FJS to Phil on Monday but was put down to a one-off but BT had the same issue today for Phil and Ceinwen. | P1 | Richard L | 25/6: Shared this with other pilot users to be warned while attempting to recreate. 26/6: Amended SEGS to translate outgoing emails to replace "exchange" addresses. | Closed | notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/8869429693EC58F980257E6F0045091D
I20 | Exchange | Phil H | 2015-07-13 | Exchange Users | License error - Product activation failed message appears when starting up outlook and in the banner of the main Outlook window | P1 | Ross | 13/7: No loss of functionality. It is because the licenses need to be applied to the on-premise Exchange Server. Likely to be user issues from 24th July (when the trial licences expire) - hence why the alerts are appearing ahead of time. 29/7: Licence properly applied, issue resolved | Closed
I21 | Exchange | Phil H | 2015-08-03 | Exchange Users | Bluecoat error for Help on Outlook. Config error or Url needing unblocking? | P2 | Katy | 03/8 - Katy has logged Assyst call. 10/08 - Call has been closed with the following comments from Rob Cawley; I have spoken to Ross Collier as he was passing to ask to test this, but he knew of the issue already. As Outlook is currently unsupported and this is an issue to be investigated by Next Gen IT project this call will be closed. Ross advises - Please raise this on the Issue Log and ensure call ref number is included I will speak to Ross in a week or so to see if this has progressed. 02/09: Ross will be progressing this shortly. Katy to check back 10th Sept. 09/09: Katy has checked back with Ross, a call is in for it. 10/09: Ross updated that changes have been implemented but did not work. Further changes will be made.
I22 | MDM | Steve | 2015-09-09 | DTM | On notes closedown a routine is triggered which captures details of software on the PC/Laptop and is reported back to DTM (Mark Davenport) | P2 |  | Losing this functionality will impact on the management of software & licences, so alternative solutions may need to be explored. 10/09: This will become an issue once everyone stops using Notes. Could be solved by using SCCM. 17/09: No changes being made by this project. Katy will discuss with Tim Bailey to see if we need to raise on the corporate risk register | New
I23 | Exchange | steve | 2015-09-09 | Exchange Users | Performance appears slow: - sent meeting invite to an external email address from both Notes & Outlook - notes arrived almost immediately - Outlook - 4 hours and not through before gave up checking | P2 |  | Users need confidence that emails issued externally will be transmitted in a timely fashion, especially when related to publications. 10/09: This is not usual…it failed to arrive. Will pass to Alberto. 17/09: Alberto has fixed, config error. Close | Closed
I24 | Exchange | Steve | 2015-09-09 | Exchange Users | Pilot users do not have the ONS directory as default (need to add it manually) | P1 | Richard L | 9/9: Outlook should have ONS directory as standard. 10/09: Close - will be populated as part of roll out, a fix has been identified. | Closed
I25 | Exchange | Steve | 2015-09-09 | Exchange Users | PGP (Pretty good Privacy) - used by approx 126 people in ONS - encrypts emails. Not sure how this works, so needs investigation | P2 |  | 9/9: Recommend speak with Andy Ledson in first instance. 10/09: Won't be integrating. Needs to be covered in training, and the work around. Some config changes will be made. PGP cannot hook into Outlook. Need to test. 17/09: Steve has spoekm to a private encrypto user, they only use it for attachments, which will work fine. Close | Closed
I26 | Exchange | Katy | 2015-09-09 | Exchange Users | Several instances where meeting invites from a Notes user to other Notes users and Outlook users were sent but the originator did not receive any responses. This was from a recurring invite but no customisation. | P2 |  | 10/09: Alberto has checked this. Responses are when the invite is sent from someone on behalf of a mailing database. The response from Outlook will try going to the mail database. Needs investigation and testing. Functionality will not be provided but when mailing database is integrated it will improve. Further testing will be needed and added to FAQs. Alberto, Rhion and Phil to test. 17/09: Carry forward, testing needed. | Investigation
I27 | Exchange | Rob Owen | 2015-09-17 | Exchange Users | When users try to open a Word document, they are unable to. There is a work around but its not ideal. Users can't open from email, you need to save the document and then open Word and then find it from there | P1 | Rob Owen
I28 | Exchange | Katy | 2015-09-17 | Exchange Users | Exchange server build configuration needs to be baselined, does anything need to be locked down? Ie; journal, RSS feeds? | P1 | Ross
Note on G4: Holding: P1 - Needs Fixing for Pilot Rollout Wave 2 P2 - Can workaround but fix during Pilot - needs fixing for full rollout Low - Nice to have, fix if time permits
Note on J4: Holding: Investigation Fix Identified Implemented Closed

## Usability Issues
To log all Usability issues found during the Pilot
Keep it Simple but we need to know what has already been spotted/fixed etc.
Id | Exchange/MDM | Logged By | Logged Date | User(s) Affected | Description | Severity | Assigned To | Comments/Progress | Status | Notes Record Link | Updated
U1 | Exchange | Phil H | 2015-06-12 | All users | Invites sent not resolving to /ONS Chair:Phil.Holding@ons.gov.uk Sent By: phil.holding@exchange.ons.gov.uk | P3 | Ross | 29/7: Not an issue, just a feature | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/3E1C947B02C1A08D80257E680037BC25
U2 | Exchange | Phil H | 2015-06-12 | All users | Attempting to import an ics exported from Notes - all recurring entries fail to be imported. | P1 | Ross | 15/6: Works for gmail but not for Exchange - needs further investigation. 29/7: Ross is investigating Cloud Migrator. Rhion has tested a Notes setting to disable custom repeats. This has been successful and will be applied before mass roll out. 1/9: Migration tool evaluation underway. This will be mitigated by the migration plan. Katy to check back next week. 09/09: Katy has checked back, a response should be available once Gavin has completed what he has been working on. 10/09: The tool works, this can be closed | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/BDC7E39EACB7682080257E6800387C71
U3 | Exchange | Phil H | 2015-06-12 | All users | Can receive, accept and reschedule part or all of a recurring invite but when the originator cancels the cancel message is not understood by Exchange and the entries remain. | P1 | Ross | As above, duplicate of U2 | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/D8B18F263ED5081D80257E6800389D87
U4 | Exchange | Ross | 2015-06-15 | All users | Notes Tables in emails appear unformatted in Exchange e.g. RFC mails | P1 | Ross | 17/6: Changed in Notes default setting resolved this. | Completed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/F6EE3729F2C2BB7D80257E6800473E9D
U5 | Exchange | Phil H | 2015-06-15 | All users | Alerts from Notes send link that Exchange can't open - Believed same for Bookmark from View. | P2 | Ross | 15/6: Would need to amend Notes to send URL as well as link as Alerts are ONS bespoke. 17/6: Live with it for the Pilot phase. 29/7: Issue resolved, fixed at Notes end, links from alerts and bookmarks can now be opened 9/9: SV - Ceinwen has reported that the Alert does not display fully in Outlook - 2nd field missing. 10/09: Lotus Notes changes needed; the fields need to be changed. 17/09: Users can add staff in the 3rd field (where link is), and remove other fields. Will communicate | Re-opened | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/03BD82C1A429F74D80257E680038E2E5 | 2015-09-09
U6 | Exchange | Sylvia | 2015-06-15 | All users | Notes users cannot read Exchange calendars and vice-versa ? | P1 | Ross | Exchange users still have a notes account but until someone migrates to Exchange they won't be able to see any Exchange calendars 17/6: Ross looking at potential workaround but can live with for Pilot. 29/7: Still ongoing. Katy will chat with Ross next week. 5/8: Katy has confirmed with Ross this is still ongoing and will come out of the migration plans he'll draw up for Exchange. 02/09: We will not be able to provide the function. Phil will discuss with Ceinwen to see if this will be acceptable. We will need to ensure there are good comms surrounding this. 10/09: No further update. A meeting is taking place 11/9. Quick migration needed. 17/09: Informing people that they can't see Outlook on Notes. Close | Close | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/2E2CB4E417EC0D5A80257E680038FB4A
U7 | Exchange | Phil H | 2015-06-15 | All users | Can still issue mails/calendar updates from Notes | P3 |  | Is this an issue ? Might prove useful (cancelling original meeting requests for example). 17/6: Live with for Pilot - hard to disable as may affect BDBs. | Completed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/00D577BF869DFFF880257E6800392219
U8 | Exchange | Sylvia | 2015-06-15 | All users | Can’t file from Outlook to a BDB directly | P2 | Derek T | Mainly a PA issue - would need to copy and manually create a BDB entry in Notes. Would lose originator metadata 17/6: Try exporting to an EML (mail) and filing that in a BDB. If works add to FAQ. 29/7: Katy will look into testing EML option. 02/09: This will not be possible to do in the same way it is now. There is a possible solution, involving a new Notes application, and it will mean the user completing a two stage process. 09/09: SV - there are 2 options in mail that we need to communicate about - Send and File as well as File has a fix been identified, or is it a workaround? 10/09: There will be a work around but will require good comms. One option is to hit FORWARD to retain email headings. 17/09: Will provide work around with detailed comms (Saving file and then putting into Notes doc if there is an attachment). | Fix Identified | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/7B7365C67EEDBF2B80257E6800394012 | 2015-09-09
U9 | Exchange | Sylvia | 2015-06-15 | All users | Can't migrate any rules from Notes to Exchange | P2 | Derek T | 17/6: Put example of a rule (file with a subject or colour for a sender) into FAQ. Will not attempt to migrate rules. 29/7: Katy will add an example to FAQ. 11/08: Katy added to Hints and Tips | Fix Identified | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/B6CE79EC48AD631580257E6800395553
U10 | Exchange | Sylvia | 2015-06-15 | All users | Using Stationary in Notes to standardise a form e.g. | P3 | Sylvia | Can this be done in Exchange ? Is there business impact. 29/7: There is a way to create Stationery in Outlook. Katy to investigate and add to FAQ 9/9 - A lot of areas use this functionality to customise their emails for specific users - suggest this area is investigated in more depth and early guidance given to users. 09/09: Katy has discussed with Ross. We are able to add signitures, colours etc but not actual template emails which people are able to do now in Notes (under Tools, Stationery). Ross has advised that this may be possible but would be client based. 10/09: There is an option called Template. Katy to investigate. There are 2 issues; migrating the existing 'stationery' emails and using the new function. Alberto and Ross could test Alex Murphys stationery. 17/09: Carry forward; Ross and Alberto to test and Katy to investigate template | Investigation | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/879BDDCD41BCCAE280257E6800397624 | 2015-09-09
U11 | Exchange | Ceinwen | 2015-06-16 | All users | Calendar meetings from Notes, when imported into Exchange via ICS transfer, appear as appointments with no attendee information. | P2 | Sylvia | 17/6: Re-test on 18/6 after Ross changed Notes default settings. 29/7: Amendments to settings has resolved issue | Closed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/B3FF065FD8E1261280257E6800398BF0
U12 | Exchange | Phil H | 2015-06-16 | All users | Using Outlook Help - unable to run help videos (popup suggests installing Silverlight, Adobe flash or Quicktime and check latest browser version. | P2 | Richard L | 17/6: Active X blocking 29/7: Katy to test on IE11 desktop. 10/08: Closing. Please see Integration Issue 21 | Investigation | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/80B8032DE9FAE3FA80257E680039C888
U13 | Exchange | Phil Morris | 2015-06-17 | All users | Sent a BDB link via http and notes to a notes document containing an excel file with readonly recommended permissions set. The file opened without the option to enter the password when via the http link but correctly when via the notes link | P2 | Phil M | Guidance should be to send a link using the notes url format to be safest. | Completed | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/08E33F5EE5CB3D8880257E680039E2F3
U14 | Exchange | Ceinwen | 2015-06-17 | All users | Notes has default access (calendars) to read only for all, Exchange is free/busy only. | P2 | Richard L and Alberto | 17/6: Set default to readonly for all (or some ?) details in standard build to match Notes behaviour. 29/7: Need to decide on policy of the setting. Needs to be done prior to roll out. Setting is on Exchange server. 02/09: Meeting title and location needs to be accessible. This will need testing. It is part of Exchange settings. 10/09: This is a design decision. Proposal should be as last week. Possibly IA to approve. Phil to take forward. Good comms needed. 17/09: Katy to email Ceinwen to ask her to ratify changing the settings to show location and title. | Investigation | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/E02D995DDEA987D380257E68003A1D68
U15 | Exchange | Ceinwen | 2015-06-16 |  | Adding CB to existing repeating Lotus Notes calendar entry - not working Creating a new repeating calendar entry however works Ken Rennoldson in LN, added CB to existing LN repeating calendar entry Sent it to me in Outlook, it did not offer me the buttons to accept etc .. see screenshots in link | P2 |  | 29/7: See if the issue still stands, Katy to recreate. 11/08: Katy tested, Notes user created meeting (with repeats) but when received by Katy, unable to respond other than to create new memo to reply with. (further screen shot added). 02/09: There is a setting in Notes, where some users (if they have the option available) can select 'Some invitees use other mail programmes'. Testing will be needed. This is a co-existence issue, with a change needed in Notes. Comms will be needed. Current repeating custom invites should transfer across. 10/09: Lotus Notes users have the option to customise invites, Outlook users cannot. The migration tool will sensibly carve up the functions so that they can be transfered across. Recurring invites that are not customised will be fine. Good comms will be needed, soon. Rhion to do further testing. 17/09: Provide comms re; switching off customisation options. Rhion has made changes and tested but not yet deployed. |  | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/A94EBE45A23AC72D80257E68004B6881 notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/C8F226351908CA0680257E9E003A8954
U16 | Exchange | Ceinwen | 2015-06-16 |  | Lotus notes updating a calendar entry - whether repeating or single - doesn't work when received by Outlook client | P2 |  | 29/7: See if the issue still stands, Katy to recreate. 11/08: Tested between Katy and Notes user. Works. 02/09: There may be issues mid-migration. Re-testing to be carried out when migration tool in place. The problem will only be solved when everyone has been migrated. | Closed - MRO | Notes://NP3APP001/80257E360052E99B/DC7D63C5D4D13EEA002565830053C117/8D7021F460BE581080257E68004BB2F5
U17 | Exchange | Sylvia | 2015-06-23 | All Notes users | When accepting a Notes invitation from Exchange, the acceptance is not resolved in Notes correctly (see link) | P2 | Rhion | 23/6: Not sure if this is a Notes or Exchange issue. 11/08: Katy has sent Sylvia a note of this and other issues, as requested, for her to discuss with Ross today. UPDATE: This will be resolved when the migration tools are in place. At the moment the two email clients are acting as separate entities and this is something we'll have to live with for the moment but should get resolved. 02/09: This could be an issue during migration. Will need to test when the migration tool is in place. 10/09: Needs further testing. 17/09: Katy will speak with Alberto to test |  | notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/C1CBD2688CBDAB9580257E6D003412CD
U18 | Exchange | Phil | 2015-06-25 | All users | Read receipts are optional in Exchange and also do not work between Notes and Exchange (and vice versa). | P3 |  | 25/6: Feature not an issue ? Not sure worth investigating further as Exchange users can unilaterally decide not to send a Read receipt anyway. 29/7: Update the Hints and Tips/FAQ with info on how these work in Exchange. 02/09: This has been turned off in Notes. Katy to add to FAQ. 10/09: For Outlook, this can be turned off? 17/09: Default is off, will keep this as it is and add to FAQ
U19 | Exchange | Phil | 2015-06-29 | All users | Brio notes booking doesn't send a mail to the Exchange mailbox (and hence calendar invite) | P1 | Sylvia | 30/6: Do we need a Brio code change for this ? 29/7: Tested again. When calendar invite sent from BRIO to Outlook user, it appears in the chairs Notes calendar, not Outlook calendar. However, it did reach the invitee. 11/08: Katy has sent Sylvia a note of this and other issues, as requested, for her to discuss with Ross today. UPDATE: Calendar entry sent to user from BRIO (need to investigate functionality further) o Option 1  Change functionality to create a mail with an ics file (or to that effect). o Option 2  Remove/disable the functionality. 02/09: Notes change needed. Will be further tested. Possibly remove this function and send Comms. 10/09: Dom is currently looking at this. 17/09: Being disabled. Katy to chase 21st Sept. Comms needed.
U20 | Exchange | Phil H | 2015-07-13 | Exchange users | Auto email requesting confirmation of attendance at events booked via a booking database does not have the buttons to be able to respond. 9/9 - Dioes Booking database put calendar entry in Outlook? - used by a number of areas | P2 | Sylvia | 29/7: Katy to discuss with Sylvia. 11/08: Katy has sent Sylvia a note of this and other issues, as requested, for her to discuss with Ross today. UPDATE: • Buttons simply don't work. o Customer Satisfaction Survey (Assyst)  Dirty Possible >> Change buttons to <a href=mail to> links. Will mean that user has to click send to confirm their choice. Change wording on mail. o Booking Databases - Confirmation of attendance mail  Possible >> Change mail to send a link to the attendance document for that person and change the form to put the actions on that form rather than in the mail. 02/09: Changes to be made in Assyst and Notes before roll out 9/9: SV - Booking databases - may need manual workaround to include in Outlook calendars. 10/09: Sylvia is currently looking at the emails received requesting confirmation of attendance. Also looking at the function of the booking database putting in a calendar entry. Perhaps creating an ICS file? Developers are looking at this. Work around; users manually enter calendar invite, comms. 17/09: Discuss with Dom, re; ICS file |  | notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/F41EF833BC817FEE80257E8200327FF3 | 2015-09-09
U21 | Exchange | Ceinwen | 2015-07-14 | Exchange users | Notes Alert doesn't include screenshot | P2 | Sylvia | 29/7: Katy to discuss with Sylvia. 11/08: Katy has sent Sylvia a note of this and other issues, as requested, for her to discuss with Ross today. UPDATE: • Action field contains effectively the body of the mail and only the link is in the body. o Can we translate the action field into the body somehow? o Possible >> Change alert form to type into Body field, but post/query save copies into the action field. o Possible (Cont) >> Tell SMTP server config (domino) to ignore any fields named action. o Possible (Mail and BDB template change). 02/09: Change in Notes needed before roll out. mail and BDB template needs changing. 10/09: Same as U5. |  | notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/50C03FF60A3D592A80257E820032A129
U22 | Exchange | Phil H | 2015-07-15 | Phil only so far | Publish outlook calendar online leads to OWA and unable to login | P2 | Richard L | 29/7: IA not happy for this to be published to internet. Richard looking into whether it can be published to Intranet. 11:08: The co-existence between Notes and Exchange will be looked at during the next phase of the Exchange migration project. This will include the ability to view calendars between the two environments. 02/09: Close. Same as U6 | Closed
U23 | Exchange | Katy | 2015-07-15 | Katy only so far | Received a Notes email to Outlook and unable to read it as S-MIME encrypted | P2 |  | 15/7: Phil received an encrypted mail which works. Will try and recreate with original sender. 29/7: Katy will find out how Ed encrypted email, as emails from Paul and Wendy worked. A call was raised, Rhion investigated, found it to be due to Ed having selected Encrypt All option. Add to FAQ. 10/09: Close after adding to FAQ. Also relates to discussions had with Steve surrounding encryption. | Closed
U24 | Exchange | Katy | 2015-07-20 | Exchange users | Unable to copy and paste a doc link from a Notes BDB into email message | P3 |  | 1 | Closed
U25 | Exchange | Katy | 2015-07-20 | Exchange users | Go into Notes BDB document, get URL and paste into email message |  |  | 22/07/15 - Works, but the Notes URL must be selected, not the http. When opening from Outlook, a pop up warning appears explaining that the link may be unsafe - put in FAQ. Interaction in any other way is not possible. 29/7: Nothing can be done to change this, will add the quick fix to Hints and Tips | Closed
U26 | Exchange | Katy | 2015-07-20 | Exchange users | Creating an Alert from Notes BDB, takes user straight to a Notes template |  |  | Will a comparable template be available in Outlook? 22/07 - No, but the Alert will still be stored in the BDB and the link can be opened from Outlook 29/7: As above, the alert will still need to be sent from Notes BDB but can be opened from Outlook. | Closed
U27 | Exchange | Katy | 2015-07-20 | Exchange users | Forwarding a Notes BDB document using the Doc Actions, Forward option takes user straight to a Notes email |  |  | Will a comparable email be available in Outlook? I.e.; can the Notes doc be forwarded via an Outlook email? 29/7: Cannot be done, as the Notes inbox will be redundant. Can simply send the URL in email from Outlook. Add to Hints and Tips | Closed
U28 | Exchange | Katy | 2015-07-20 | Exchange users | When receiving emails from Notes users to Outlook inbox, Notes BDB doc links can be opened |  |  | Have tested this with several emails, ie; ERMS emails, an email containing DSE assessment document . 29/7: Closing as there are no issues | Closed
U29 | Exchange | Katy | 2015-07-20 | Exchange users | If there is a document, such as a DSE Assessment, that an Outlook user wishes to send via email, there is no option to Get URL and Copy doc link will not work |  |  | 22/07/15 - Right click on the document, go to Properties, Document and select the <+> tab and the URL is available in the Identifier field | Closed
U30 | Exchange | Katy | 2015-07-20 | Exchange users | When a calendar invite (set up in Notes but copied over to Outlook) is approaching, the reminder only pops up in Notes | P3 |  | 29/7: Recreate this. Get an invite sent from Notes account. Check the reminder option; is it functioning? 11/08: Reminders for meetings, appointments etc set up in Notes that are copied across are now appearing in Outlook. | Closed
U31 | Exchange | Katy | 2015-07-20 | Exchange users | When a call is closed in Assyst, the customer receives an email to ask for feedback on how the call was dealt with. In Notes emails there are radio buttons to register the response, but in an Outlook email, there is not the option to do this. There is the option to go to the Web browser page which does give the option to click a radio button, however, this then throws up warnings about the website opening web content that is outside of protected mode. There is the Allow or Do Not Allow option. | P2 |  | 29/7: Will be an issue for mass roll out. Need a way for Service Mgt groups to get feedback. Sue Fendall may be able to help. 5/8: Katy has emailed Sue Fendall, explaining that there is the option to open the email in a web browser page, which then allows the user to select a hotspot button. However, when user clicks on a button, a new email is automatically generated. It is addressed to IM Questionnaire Responses, and in the subject line, the call reference number and feedback option (numerical, not actual wording) are automatically imported and the body of the email is blank. Awaiting response. 11/08: This is similar to U20. It's a FJS change that needs discussing with Phil Mann and/or his colleagues. It will be a change and a change in operation to be implemented. 02/09: Same as U20
U32 | Exchange | Katy | 2015-07-20 | Exchange users | How will users personal address book migrate across? | P2 |  | 22/07/15 - Being looked at. Still some issues with regards to importing. 1/9: Needs to be a part of the migration tool evaluation. 10/09: This will be seamless, providing that users are logging in and out of Notes correctly. Comms needed.
U33 | Exchange | Katy | 2015-07-20 | Exchange users | In Notes, there is an option to File in BDB, whereby you can select a BDB to save the email too. Can this be done in Outlook? |  |  | 22/07/15 - If this function is not available to begin with, it will have to be done via copy and paste and creating a new document. If this is not an appropriate quick fix for users, increasing quota allowances can be looked at. 29/07: Duplicate of U8 | Closed
U34 | Exchange | Katy | 2015-07-27 | Exchange users | When creating a repeat calendar entry in Outlook, when you need to amend it there is an option to make the amendments for all occurrences, but you can't actually do so. |  |  | 29/7: Add to Hints and Tips. You can change all occurrences via the Recurrence function. | Closed
U35 | Exchange | Katy | 2015-08-24 | Exchange users | Jon Blake has been experiencing difficulties when trying to send Word docs via Outlook. It has been happening intermittently over a few days. Whether it is sent from Word or attaching the Word doc to an Outlook email, he gets the same error message (see screenshot) | P2 | Investigate | 24/8: Katy has discussed with Ross, its thought it’s a network issue as opposed to an Outlook problem. Have let Jon know to continue with work around (sending docs via Notes email account) and Ross will look into. 02/09: When Jon has moved to Windows 10 this can be re-tested. 10/09: Richard Lake has experienced similar issues. He is looking into this. 17/09: Katy to chase Richard |  | notes://NP3APP001/80257E360052E99B/DDCD8D7CA92BFCF68025684F0055F3F1/7AA827EB43E4BA9280257EAB004A405A
U36 | Exchange | Katy | 2015-09-02 | Exchange users | There is a function currently in Notes, that will need to function in Outlook ; being able to amend and send auto responses sent to departmental inboxes (ie; mass mailing) | P2 |  | 02/9: A call has been logged (R392169). Latest activity on call; This is regarding your Assyst request for information R392169, and suggestions for replacing MailChimp. Lotus Notes lead Sylvia Stevens, Rhion Parsons and other Notes administrators, Ross Collier and I have discussed. We recognise that there is likely be even broader need for a mass-mailing solution for the organisation. However, owing to the already busy transformational time for many ONS systems including our mailing systems, the introduction of any newer mass-mailing solution will become a consideration for Gap Analysis during the next one to two months. My conversations today are being shared with the relevant Project Manager along with your call ref. and your Assyst call will be held for continued visibility in the Software Approvals queue as a requirements marker. In the meantime, please be aware that the Lotus Notes Team are able to handle your bulk requests if the work can be organised to allow sufficient time to allocate their resource. Work requests need 5 days notice, their resources are scarce at this busy time and this is their SLA. And to provide another option, the published intranet how-to notes around using email-merge are available here: http://intranet/workinginons/howtoguides/itservices/itiwantoguides/know-to-use-the-email-merge-facility-in-notes.asp This is restricted to sending 150 at a time and the size of attachments is restricted, so if a large number of mails needed to be sent they would simply need to be split into bundles. 02/09: There is another work around; using a bespoke application. Will be captured in the next phase. |  | Investigate
U37 | Exchange | Katy | 2015-09-02 | Exchange users | User has raised concern regarding email distribution. They send thousands of emails per week and want to ensure the transition is seamless. They want to be able to test beforehand (Martin Nicholls. Awaiting more info from him). | P2 |  | 02/09: Need to check that the user has a bespoke app in Notes (for sending the emails). If so, this will not be affected. This will be migrated as part of application migration exercise. 9/9: SV - met with martin nicholls - they use an application to manage bulk mailings - this automatically creats an email in Notes using pre-defined stationery. It is also crucial to retain the logs of who mails have been sent to for resolving queries. This is linked to the publication cycle where emails need to be sent out by 9.30 for specific releases. Quite Crucial 10/09: Pending confirmation, this should work. Ross confident it will be fine. 17/09: Not migrating this database. |  | Investigate | 2015-09-09
U38 | Exchange | Katy | 2015-09-02 | Exchange users | Letterheads - Currently, in Notes it is possible to add a logo by the mail header. This is done through the design of the mail box and there are no plans to change mail then we won't add any new ones. Considered looking at Outlook to see if they could be added as some sort of stationary but Neil has had a go and couldn't find anything that he could put in place. There will have to be a different method used if people want to add some sort of identity to their emails. I'm guessing footers or signatures will have to contain logos. | P2 |  | 17/09: Same as stationery, covered elsewhere. | Closed
U39 | Exchange | Steve | 2015-09-09 | Exchange users | Outlook does not have an option to mark emails Official Sensitive (well not in the version I have) | P2 |  | 09/09There are options to apply a sensitivity rating to an email, which is a drop down list - potential to amend this? 10/09: Only possible by customising Outlook…would like to avoid this. Can be typed in manually. Cover in Comms. 17/09: Phil to verify with Ceinwen. | New | Investigate
U40 | Exchange | Steve | 2015-09-09 | Exchange users | Stationery - linked to U37 &U38. A number of areas use Stationery to customise emails to external users. Guidance should be provided to users on how to do this in Outlook | Low |  | Covered elsewhere | New
U41 | Exchange | Steve | 2015-09-09 | Exchange users | Users email addresses appear to lose the .gsi suffix. This should be pointed out to people - no expected change in functionality so long as processes exist for mail forwarding | Low |  | Include in training 10/09: Dependent on how a user was set up. Will need careful Comms | New
U42 | Exchange | Steve | 2015-09-09 | Exchange users | Outlook does not have same functionality in Calendar to allow users to copy an existing meeting into a new meeting request with same users | Low |  | Include in training. 10/09: Covers with Comms | New
U43 | Exchange | Steve | 2015-09-09 | Exchange users | Settings to allow users to automatically accept (or decline) meeting invites are quite well hidden. Suggest guidance on how to do this | Low |  | Include in training. 10/09: Covers with Comms and FAQ (training) | New
U44 | Exchange | Steve | 2015-09-16 | Exchange users | Users unable to secure emails containing sensitive information from others who have delegate access to their emails 21/9 SV: Users will need to be able to identify those emails that are not being moved across due to encryption so theya are able to deal with them accordingly | P2 |  | This is a feature used across ONS, and particularly HR, Contracts & Finance (Customer First). Have explored the 'Private' option but this does not apply to emails if user selects Encryption the error message displayed - get a Digital ID. 17/09: Testing required | New | urgent investigation | 2015-09-21
U45 | Exchange | Steve | 2015-09-16 | Exchange users | Junk Mail - a meeting invite sent to me from a Notes user ended up in my Junk Mail folder | P2 | Alberto | Needed to move it to inbox (not a straightforward process in itself). 17/09: Exchange server setting, Katy to discuss with Alberto | Investigation
U46 | Exchange | Katy | 2015-09-16 | Exchange users | Users will not be able to send or receive PC faxes | P2 | Ross | Ask Ross for more info | Investigation
U47 | Exchange | Steve | 2015-09-17 | Exchange users | Unable to sign in to the on-line version of outlook (Outlook web app) 21/9 SV: what credentials should be used | P3 |  | Is this a function that is to be available to users & if so, what benefit does it offer to the outlook client? | New |  | 2015-09-21
U48 | Exchange | Steve | 2015-09-17 | Exchange users | New email address for outlook does not match my existing notes email address - Steven.Vickers compared to steve.vickers | P2 |  | This looks like the migration has been done using the NCD values which may result in differences to existing email addresses as in my example (or has this been done manually) - ideally do a test migration of names and look for differences to existing values - if values are changing and we are not to do anything about it we'll need to let those effected know about it | New
U49 | Exchange | Steve | 2015-09-21 | Exchange users | Migrating Calendar entires that are encrypted - it is expected that these will not be migrated as encrypted emails are also not migrated - users need to be able to identify which entires may be effected - links to U44 | P2 |  | Agree how are users able to identify encrypted meeting requests that have not been migrated across - it cannot be assumed that any histopric meetings are not still used by individuals as a point of reference for information (i.e. if the approach is to treat this information as redundanct we should be looking to provide guidance on how users can (1) identify and (2) manage this information if necessary | New
U50 | Exchange | Steve | 2015-09-21 | Exchange users | It has been suggested that after 2 - 3 weeks emails & calendar entries in Notes will be deleted - users have suggested this may not be long enough for individuals to manage their emails, especially as there will be a new process for filing in bdb & if encryopted emails are not being brought across | P2 |  | Perhaps consider ealy warning, asking users to start filing or deleting their emails now? | New
U51 | Exchange | Steve | 2015-09-21 | Exchange users | Document links inserted to Notes calendar entries are not appearing in the Outlook meeting invite (they do appear in an email from Notes to Outlook) In the example of invite received by steve Vickers, the doc link appeared as a .gif attachment (which when opened was the same image as that received if sent by email) | P2 |  | Links to U28 Workaround might be to include URLs (shortened links / hyperlinks) | New
U52 | Exchange | Steve | 2015-09-21 | Exchange users | Some areas have their own Address books which are managed using a Notes database Digital Publishing use this function daily | P2 |  |  | New
U53 | Exchange | Alberto Igbinedion | 2015-09-22 | Exchange users | Email that you send on behalf of someone is not saved in their Sent Items folder | P2 |  | Cause This DelegateSentItemsStyle registry value was not implemented in the RTM release version of Outlook 2010. ( Ref: https://support.microsoft.com/en-us/kb/2181579 ) | New
Note on G4: Holding: P1 - Needs Fixing for Pilot Rollout Wave 2 P2 - Can workaround but fix during Pilot - needs fixing for full rollout Low - Nice to have, fix if time permits
Note on J4: Holding: Investigation Fix Identified Implemented Closed